Phase 4 Sprint — Live Operations Integration

Climate & Crisis Ops Command · Future Caribbean · New Providence pilot

Document date: August 15, 2026

# Goal

CCOC stops being a demo shell and runs on real feeds, real unit locations, real hazard data, and real outbound COMMS — with HITL still gating sends, but sends actually happening after approval.

# Where You Are Today

Phases 2–3b built the coordination workflow (agents, HITL, audit, hazard fusion, map). Almost every external integration follows the same pattern:

| Pattern | What exists | What's missing |
| --- | --- | --- |
| Webhook ingest | Real endpoints (CAD, public safety, flood/wind ingest) | Operators must push data; no pull/poll adapters for most feeds |
| REST polling | Env vars declared (CAD_FEED_URL, PUBLIC_SAFETY_URL) | No fetch code — label only |
| Metadata probe | GLOFAS CDS + JBA/Fathom verify keys | No GRIB/vendor forecast download in-app |
| Outbound COMMS | Draft generation + triple/extended HITL | No SMS/email gateway — audit says demo: send blocked even after full approval |
| Dispatch manifest | Hardcoded data/sample-dispatch.csv | No operator manifest adapter |

NHC weather RSS is the one feed that can already be live (NHC_LIVE=true).

# Sprint Principles

- Agency wins — Bahamian EOC/public works flood GIS beats model layers

- HITL mandatory — nothing auto-sends; approval triggers real delivery

- Not 911/CAD replacement — read-only situational + NEMT handoff write-back only

- Design-partner gated — live ops requires operator agreements + API keys before code can be tested end-to-end

- Sovereign path preserved — air-gap bundles still work when outbound APIs are blocked

## Parallel Workstream 0 — Credentials & Design Partners

Start procurement/onboarding before engineering finishes adapters. These block live testing.

### Credential acquisition checklist

| Credential | How to get it | Env var(s) | Blocks |
| --- | --- | --- | --- |
| Copernicus CDS / GLOFAS | Register at cds.climate.copernicus.eu | GLOFAS_CDS_KEY | Live river/discharge gap-fill |
| JBA Flood Foresight | Contact JBA Global Resilience — evaluation for New Providence bbox | URBAN_FLOOD_API_KEY, URBAN_FLOOD_API_URL | Live urban pluvial polygons |
| Fathom Global (alternate) | Commercial email + pilot contract at fathom.global | Same as JBA with URBAN_FLOOD_VENDOR=fathom | Urban flood if JBA unavailable |
| Twilio (or carrier) | Account + SMS number + A2P registration | TWILIO_* (new) | Driver SMS after HITL |
| Email provider | SendGrid / AWS SES / operator SMTP | COMMS_EMAIL_* (new) | Hospital COMMS-03 bulletins |
| NEMT dispatch API | Nassau Metro or pilot NEMT operator | DISPATCH_FEED_URL (new) | Live trip manifest |
| CAD / AVL feed | County CAD vendor or NEMT CAD REST export | CAD_FEED_URL | Live unit/run overlay |
| Police/fire AVL | Royal Bahamas Police / EOC AVL export | PUBLIC_SAFETY_URL | Live unit pins on map |
| Agency GIS webhook | NEMA / public works FeatureServer or push webhook | FLOOD_DEPTH_PATH + ingest auth | Authoritative flood depth |
| Wind exposure GIS | NEMA / NWS wind field or agency polygon export | WIND_EXPOSURE_PATH + ingest | Gust-zone trip cross-ref |
| ESRI corridors | Agency FeatureServer URL | ESRI_CORRIDOR_URL | Live corridor status |
| Hospital transport desk | PMH / Doctor's Hospital EMS liaison API | TRANSPORT_DESK_URL | Bed pressure, handoff queue |
| Institutional signals | OCHA / GFDRR / regional feed | INSTITUTIONAL_FEED_URL | Multi-feed monitor brief |
| LLM (optional) | Groq / OpenAI / Ollama local | LLM_* | Richer COMMS prose only |

### Design partner agreements needed

- ☐ NEMT operator — dispatch manifest + driver phone numbers + SMS consent

- ☐ Hospital liaisons — COMMS-03 email recipients + approval workflow

- ☐ EOC / NEMA — agency flood + wind GIS webhook push OR FeatureServer access

- ☐ CAD vendor — read-only REST export spec (runs, units, lat/lon, status)

- ☐ Public safety — read-only unit AVL feed (no dispatch authority in CCOC)

- ☐ JBA or Fathom — New Providence urban core license + API docs

- ☐ Legal — SMS consent, PHI handling, data retention for audit JSONL

# Sprint Tracks & Calendar (20 working days)

Four parallel tracks. Days are suggested sequencing within each track.

| Track | Days | Focus |
| --- | --- | --- |
| A — Outbound COMMS | 1–10 | SMS gateway, hospital email, HITL release hook, delivery audit |
| B — Live Dispatch/CAD/Public Safety | 1–12 | Dispatch REST, CAD poller, police AVL, transport desk write-back |
| C — Live Hazard & Weather | 1–14 | Agency flood/wind, GLOFAS GRIB worker, JBA fetch, ESRI corridors, multi-feed signals |
| D — Production Hardening | 1–15 | Webhook auth, cron/schedulers, live deploy profile, acceptance tests |

# Track A — Outbound COMMS (Days 1–10)

Current: src/agents/action/pack.js generates COMMS-03 bulletins + driver SMS drafts. src/hitl/index.js approves but records demo: send blocked.

### Day 1–2: COMMS transport layer (new module src/comms/)

| Provider | Use case | Suggested env |
| --- | --- | --- |
| Twilio SMS | Driver reroute / delay notices | COMMS_SMS_PROVIDER=twilio, TWILIO_* |
| SendGrid / SES | Hospital COMMS-03 bulletins | COMMS_EMAIL_PROVIDER, COMMS_EMAIL_FROM |
| Webhook fallback | Operator-owned gateway | COMMS_WEBHOOK_URL |

- sendDriverSms({ to, body, packId, tripId }) with delivery receipt

- sendHospitalBulletin({ to, subject, body, hospitalId, packId })

- Idempotency key per HITL release (no double-send on retry)

- Scope guard: refuse send if draftOnly: true or HITL incomplete

### Day 3: HITL release → send hook

- On final approval: set draftOnly: false, call src/comms/dispatch.js

- Audit: comms_sent with provider message IDs (replace demo: send blocked)

- UI: remove DEMO send banner; show delivery status per bulletin/SMS

### Day 4–5: Recipient resolution

- Map trips → driver phone from live dispatch manifest

- Map hospitals → liaison email from operator config

- Validate E.164 phone format; block send if missing consent flag

### Day 6–7: Delivery audit + operator controls

- GET /api/comms/status — last sends, failures, retries

- POST /api/comms/retry/{messageId} — operator retry

- Kill switch: COMMS_SEND_ENABLED=false (default in dev; true only in production)

### Day 8–10: End-to-end COMMS acceptance

- ☐ Pipeline → HITL triple approve → SMS arrives on test phone

- ☐ COMMS-03 email arrives at hospital liaison inbox

- ☐ Failed send surfaces in UI + audit without silent drop

- ☐ Extended HITL (5-role) path also triggers send

- ☐ Runbook: never auto-send from model_estimated zones alone

# Track B — Live Dispatch, CAD & Public Safety (Days 1–12)

Current: Static CSV/JSON samples. Webhooks work but nothing polls REST feeds.

### Day 1–3: Live dispatch manifest adapter

- New src/dispatch/adapters/rest.js

- Env: DISPATCH_FEED_URL, DISPATCH_FEED_POLL_MS, DISPATCH_API_KEY

- Normalize operator JSON/CSV → existing trip schema

- Acceptance: At-risk trip count changes when operator updates manifest

### Day 4–7: CAD REST poller

- New src/cad/adapters/rest.js (CAD_FEED_URL already declared but unimplemented)

- Poll runs, units, lat/lon, status, incident/run IDs

- Acceptance: Unit pin moves on map when CAD status changes

### Day 8–10: Police/fire AVL poller

- New src/public-safety/adapters/rest.js

- Env: PUBLIC_SAFETY_URL, PUBLIC_SAFETY_POLL_MS, auth headers

- Acceptance: Police unit location on map matches AVL feed within poll interval

### Day 11–12: Transport desk + NEMT write-back

- Implement TRANSPORT_DESK_URL REST poller

- Upgrade write-back to real CAD assignment API when NEMT_WRITEBACK_URL configured

- Acceptance: Handoff accept updates operator CAD run ID

# Track C — Live Hazard & Weather Data (Days 1–14)

### Day 1–2: Agency flood + wind live operations

- Webhook ingest already built at POST /api/geo/hazards/flood/ingest and /wind/ingest

- Operator runbook for NEMA/public works push cadence

- Webhook authentication; stale detection alerts

- Acceptance: Agency flood polygons from live push; agency_confirmed confidence

### Day 3–8: GLOFAS live GRIB pipeline

- Complete Python sidecar: CDS retrieve → NetCDF/GRIB → discharge grid JSON

- Cron: npm run geo:glofas-fetch every 6–12h at L2+

- Node convert: grid → glofas-nassau-latest.json

- Credentials: GLOFAS_CDS_KEY (see docs/glofas-cds-setup.md)

- Acceptance: Fresh clip without demo fallback; stale warning clears after fetch

### Day 3–7: JBA / Fathom live forecast download

- Implement vendor-specific forecast fetch once JBA provides API URL + key

- Download depth grid → urban-flood-grid-*.json → convert via urban-flood-convert.js

- See docs/urban-flood-vendor-setup.md

- Acceptance: URBAN_FLOOD_VENDOR=jba + live key → commercial_model zones without demo clip

### Day 9–10: Wind exposure from operational source

- Agency wind polygon webhook, NWS/NHC wind field worker, or manual EOC push

- Acceptance: Gust-zone trip exposure updates when NHC escalates to L3+

### Day 11–12: ESRI FeatureServer live pull

- Implement ESRI_CORRIDOR_URL fetch in src/geo/esri.js

- Corridor CLOSED/RESTRICTED status drives triage reasons

### Day 13–14: Multi-feed signals

- Wire INSTITUTIONAL_FEED_URL REST adapter

- Monitor brief cites live OCHA/GFDRR when available

# Track D — Production Hardening (Days 1–15)

### Day 1–3: Security

- Webhook HMAC signing: X-CCOC-Signature with WEBHOOK_SECRET

- API key for ingest endpoints: INGEST_API_KEY

- Role-based HITL auth (operator tokens per role)

- Secrets via env only — never commit

### Day 4–7: Schedulers & health

- Cron/systemd timers for GLOFAS, urban flood, CAD/dispatch poll, signal refresh

- GET /api/health/live — per-feed freshness

- Alert when any critical feed stale beyond threshold at L2+

- Document in docs/live-ops-runbook.md

### Day 8–10: Production deploy profile

Extend src/deploy/sovereign.js → src/deploy/live.js with checks:

| Check | Pass criteria |
| --- | --- |
| COMMS provider configured | Twilio/email probe succeeds |
| Dispatch feed | Last poll < 5 min |
| CAD feed | Units > 0 or explicit empty OK |
| Agency flood | Webhook received in last 24h OR stale alert acknowledged |
| GLOFAS / urban | Live fetch OR air-gap clip < stale hours |
| HITL | Send enabled only when COMMS_SEND_ENABLED=true |
| Audit | AUDIT_PERSIST=true |

### Day 11–15: Live acceptance test suite

- ☐ Live NHC escalation triggers L2 pipeline

- ☐ Live dispatch trip appears in triage rank

- ☐ CAD unit cross-ref matches run ID

- ☐ Agency flood suppresses GLOFAS on overlap

- ☐ HITL approve → SMS delivery receipt in audit

- ☐ Feed failure → graceful degrade + operator alert (no crash)

# Master .env Additions (Phase 4)

Add to .env.example when implementing:

# --- Phase 4 Live Ops ---
COMMS_SEND_ENABLED=false
COMMS_SMS_PROVIDER=twilio
TWILIO_ACCOUNT_SID=
TWILIO_AUTH_TOKEN=
TWILIO_FROM_NUMBER=
COMMS_EMAIL_PROVIDER=sendgrid
COMMS_EMAIL_FROM=
SENDGRID_API_KEY=
COMMS_WEBHOOK_URL=
DISPATCH_FEED_URL=
DISPATCH_FEED_POLL_MS=60000
DISPATCH_API_KEY=
CAD_FEED_POLL_MS=30000
CAD_API_KEY=
PUBLIC_SAFETY_POLL_MS=30000
PUBLIC_SAFETY_API_KEY=
TRANSPORT_DESK_POLL_MS=120000
NEMT_WRITEBACK_URL=
WEBHOOK_SECRET=
INGEST_API_KEY=
OPERATOR_CONFIG_PATH=data/operators/nassau-metro.json

Existing GLOFAS/JBA vars from .env.example lines 83–118 remain required for hazard layers.

# Definition of Done — Actually Works

The sprint is complete when an operator can run this live drill without demo data:

- Storm escalates — NHC live feed (or operator inject) → L2+

- Real trips load — dispatch manifest from NEMT operator API

- Map is live — CAD units + police AVL + agency flood + (GLOFAS or JBA) merged

- Agents run — Monitor brief cites live feeds; Triage ranks real at-risk trips; Action drafts COMMS-03 + SMS

- HITL approves — NEMT supervisor + hospital liaisons sign off

- Messages send — Driver SMS delivered; hospital email delivered; audit records provider IDs

- No silent failures — stale feed alerts visible; degraded mode documented

- Sovereign still works — air-gap profile passes deploy check without outbound APIs

# Risk Register

| Risk | Mitigation |
| --- | --- |
| JBA API URL not public — design-partner only | Start JBA contact Day 0; use Fathom alternate or licensed GeoJSON export + webhook ingest |
| CAD vendor won't expose REST | CSV drop folder watcher or webhook push from operator middleware |
| SMS regulatory (consent, A2P) | Legal review Day 0; test with operator-owned numbers first |
| GLOFAS GRIB processing heavy | Python sidecar on connected staging; sovereign uses pre-download clip |
| Scope creep into 911/CAD replacement | Keep scope guards; write-back limited to NEMT handoff accept |

# Recommended Sequencing (small team)

### Week 1 (unblock visible value)

- Credentials procurement (parallel)

- Dispatch REST adapter

- CAD REST poller

- COMMS transport + HITL release hook

### Week 2 (hazard truth)

- Agency flood/wind webhook ops + auth

- GLOFAS GRIB worker

- JBA fetch (when key arrives)

### Week 3 (complete picture)

- Police AVL poller

- ESRI live corridors

- Production hardening + live acceptance tests

# Files You'll Touch (engineering map)

| Area | Existing | New / extend |
| --- | --- | --- |
| COMMS send | src/hitl/index.js, src/agents/action/pack.js | src/comms/*, src/routes/comms.js |
| Dispatch | src/dispatch/index.js | src/dispatch/adapters/rest.js |
| CAD | src/cad/index.js, adapters/csv.js | src/cad/adapters/rest.js |
| Police | src/public-safety/index.js | src/public-safety/adapters/rest.js |
| GLOFAS | src/geo/glofas-cds.js, scripts/glofas-grid-from-nc.py | Complete Python worker + cron |
| Urban flood | src/geo/urban-flood-vendor.js | Vendor forecast download |
| ESRI | src/geo/esri.js | FeatureServer fetch |
| Security | src/server.js | Webhook auth middleware |
| Deploy | src/deploy/sovereign.js | src/deploy/live.js |
| Docs | existing setup docs | docs/live-ops-runbook.md |
| Tests | tests/* | tests/live-comms.test.mjs, feed poller tests |

# Summary

Phases 2–3b built the command surface; Phase 4 wires the pipes and turns HITL approval into real-world action. This sprint closes the gap between production-shaped demo and production-operational.